# CodeTech Team & Project WBS for Rofane QA Lifecycle Management System

## CodeTech Team & Responsibilities

| Name | Role | Responsibilities |
| --- | --- | --- |
| Rhulani | Team Lead / Project Manager | Oversees project, manages timelines, assigns tasks, communicates with Rofane, ensures delivery and quality. |
| Thabiso | Backend Developer | Builds database, APIs, authentication, and integration logic. |
| Tino | Frontend Developer | Designs user interface, integrates backend APIs, ensures responsive layout. |
| Lekgotla | System Admin | Handles deployment, server setup, user accounts, and maintenance. |
| Galaletsang | Business Analyst (BA) | Collects requirements, documents processes, and ensures business needs are met. |

## Work Breakdown Structure (WBS)

| Task Name | Description | Duration | Predecessors | Team Members | Resources Needed |
| --- | --- | --- | --- | --- | --- |
| 1. Project Initiation | Define scope, goals, and deliverables for Rofane QA System. | 5 days |  | Rhulani, Galaletsang | Project brief, stakeholder meetings |
| 1.1 Requirements Gathering | Meet Rofane to understand QA problems and needs. | 4 days | 1 | Galaletsang, Rhulani | BRS documents, notes |
| 1.2 Scope & Planning | Finalize plan, assign roles, and prepare timeline. | 3 days | 1 | Rhulani, Galaletsang | Planning tools |
| 2. System Design | Design UI mockups, database, and architecture. | 6 days | 1.2 | Thabiso, Tino, Galaletsang | Design tools, ERD, Figma |
| 2.1 UI Wireframes | Create layouts for dashboards, forms, and reports. | 4 days | 2 | Tino, Galaletsang | Figma or Draw.io |
| 2.2 Database Design | Design database tables for users, cases, bugs, reports. | 5 days | 2 | Thabiso | MySQL, ERD tool |
| 3. Development | Build and integrate frontend & backend features. | 15 days | 2.1, 2.2 | Thabiso, Tino | VS Code, Git, XAMPP |
| 3.2 Test Case & Execution Module | Allow users to add, execute, and view test cases. | 8 days | 3 | Thabiso, Tino | PHP, JavaScript |
| 3.3 Bug Tracker | Module for logging, assigning, resolving bugs. | 8 days | 3 | Thabiso, Tino | DB, workflow rules |
| 3.4 Dashboard & Reports | Build real-time dashboard and daily reports. | 7 days | 3.3 | Thabiso, Tino | Chart.js, PHP |
| 4. Testing | Verify features, fix bugs, retest. | 10 days | 3.4 | Rhulani, Galaletsang | Test cases, QA tools |
| 4.1 UAT with Rofane | Client testing and sign-off. | 6 days | 4 | Rhulani, Galaletsang | Demo environment |
| 5. Deployment | Host and configure system for live use. | 5 days | 4.1 | Lekgotla, Rhulani | Hosting server, FTP |
| 5.1 Training | Train Rofane users on system usage. | 3 days | 5 | Rhulani, Galaletsang | User manual, guide |
| 6. Support & Maintenance | Fix bugs, monitor system, and make updates. | 10 days | 5.1 | Lekgotla, Thabiso | Ticketing tool, logs |